## 2019 NCCUSL activities
NorCal Chapter of US Lacrosse, Inc.
| 2019 key NorCal Chapter activities/initiatives | Objective | Primary person responsible | Planned Time frame | Projected Income | Projected Expense | Comments
1 | California Lacrosse Convention | Provide additional learning opportunities for coaches and administrators | Carlos | Jan 26 or 27 | 8250 | 8250 | Objective is to at least break even. Jan 6 or 7 look best. Evaluate venues now. Nolan and Godfrey indicate that they may have some men's game speakers lined up. DTA to review. Not sure if Nolan can line up women's game speakers. May need help.
2 | Additional onsite coach training | Provide additional onsite training for coaches | Don & ? | As requested |  | 600 | Don to promote this support at NCJLA delegates meeting. Utilize Lorne Smith, ADVNC, Encore, Tenacity and other professional coaches and organizations; 3 clinics; need to find a reliable coordinator familiar with good professional coaches
3 | Lacrosse Town Hall meeting (s) | Develop understanding of LLO's, HS CIF and other local lacrosse organizations challenges in order to develop chapter support activities | Don | June |  | 600 | Meeting room and refreshment costs included in travel and meeting expenses. One meeting could be held at NCJLA's summer workshop.
4 | Grant for local NorCal Women's team | Grant monies to partially cover costs associated with sending 2 teams. | Laura | April |  | 1350 | Cover regsitration fee for one team
5 | Outreach | Provide sticks and guidance to individuals and programs that want to have clinics and or establish or expand lacrosse in their geography; Hold chapter Learn to Play clinics in target areas for development | Cathy, Phil, Laura, Ian & Don | Year round |  | 3700 | Direct costs include storage unit, shipping sticks and new stick purchases.
6 | Diverstiy and inclusion | Lauren to flesh out | Lauren, Carlos |  |  |  | Provide assistance or apply directly to USL and other organizations to obtain funds for D&I grants. Provide guidance on expanding D&I for exisiting organizations as well as assisting with the start up of new organizations.
7 | Non traditional area sport development | Establish one new lacrosse program in a non traditional area | Cathy Reed, Phil Bodenhorn, Carlos Trjillo & Don | Ongoing |  |  | Reach out to Lacrosse community to determine which programs could benefit with financial or material support.
8 | National team clinics | Provide additional training opportunities for boys & girls in the chapter; expand awareness of chapter's role in supporting lacrosse | TBD | January 25/26/27 for US National women's team event |  |  | Work with USL to find and/or support local USL national team performance and training clinics as well as other supporting events such as fund raising dinners and events. No income or expenses budgeted.
9 | Support USL All American process | Support USL All American process so local athletes obtain recognition | Jen Lee/Nick Juri/Jerem Stothers/Bruce Dini; Chapter publicity - Torri H | May - July |  |  | Receipents announced and published on the NorCal website and newsletter in June.
10 | Maintain website & send out periodic newsletters (6-8) | Broad communications | Torri Horowitz; Dan Miller; Don Aiello | Jan-Dec |  | 300 | Website - load material and programs; 8 newsletters
11 | Participate in key league and local lacrosse events, e.g., Girls Play Day or equivalent (Davis and/or TI); NCJLA end of season events (May); NCJLA Delegates mtg (Sept); | Develop and expand awareness of Chapter and USL programs and services | Chapter board members as available | Feb, Mar, May, Sept |  | 1000 | Costs would include travel and meeting expenses. Moving the Chapter booth; Production of flyers and chapter logoed giveaways. Stocked items from 2016 would carryover/be available
12 | Additional board members and committee volunteers | Add 1-3 more board members and key activity volunteers. Fund raising & Sponsorship; POCO rep; HS boys and girls reps; board development chair; Events coordinator; | Don | Ongoing |  | 600 | Shirts, hats, awards, meals
2018 activities discontinued for 2019 due to USL restructing, UC spinout or timing
| Support Officials' evaluations and officials trainer development programs | Provide funds to men and women officials' organization so trainer officials can take time to evaluate on field officials with the expectation that the level of officiating overall rises. |  |  |  |  | Support for Officials organizations will come directly from USL through the officials'
| HOF recognition dinner | Recognition of HOF recipients; further opportunity to expand the awareness of Chapter |  |  |  |  | No HOF event in 2019; combine with class of 2020 for event in 2020
| Oversee NorCal Chapter Umpire Committee | Continue UC operations under the chapter through mid-year and then plan to spin it out to its own organization. |  |  |  |  | NCCUSL UC spun out in August 2018 will no longer be under NCCUSL.
Advocate for Educations and Training
Support Local Lacrosse Organizations
Fuel the Growth of the Sport
Promote USL Brand & Drive Member Value Awareness
Other