## 2018 NCCUSL activities
NorCal Chapter of US Lacrosse, Inc.
| 2018 key NorCal Chapter activities/initiatives | Objective | Primary person responsible | Person(s) who did or will coordinate | Planned Time frame | Actual Date(s) | Projected Income | Projected Expense | YTD Actual Income | YTD Actual Expense | Original Comments | Updated comments
1 | California Lacrosse Convention | Provide additional learning opportunities for coaches and administrators | TBD - Initial leadership interest from Nolan Godfrey (Novato HS) & Jim Kircher (Petaluma club) |  | Jan 6 or 7 |  | 8250 | 8250 | 0 | 0 | Objective is to at least break even. Jan 6 or 7 look best. Evaluate venues now. Nolan and Godfrey indicate that they may have some men's game speakers lined up. DTA to review. Not sure if Nolan can line up women's game speakers. May need help. | No convention in 2018 since no one stepped up to organize it
2 | CEP sessions; 8 level 1's (new short course) for men and women; 1 level 2 | Provide CEP clinics to support league and national requirements for certified coaches. 8 new level 1 clinics; 1-2 Level 2's | Lou Biaggi | Don and Laura | Jan/Feb |  |  | 3800 |  | 1950 | Chapter in conjunction with NCJLA to reach out to clubs to determine interest. Only establish clinics if interest from a club and NCJLA support. | CEP Level clinics – Level 3, Dec 2 & 3, San Rafael – 13; Level 1’s: December 16th, Petaluma - 38; Jan 13th, San Francisco - 15; Jan 28 – Sacramento - 45; Feb 10th, Folsom - 35; Feb 11th, Menlo Atherton - 9; March 4, Pleasanton – 27… 169 Level 1 trained coaches
3 | Additional onsite coach training | Provide additional onsite training for coaches | TBD | Don | As requested |  |  | 600 |  | 0 | Utilize Lorne Smith, ADVNC, Encore, Tenacity and other professional coaches and organizations; 3 clinics; need to find a reliable coordinator familiar with good professional coaches | No requests, YTD.
4 | Outreach | Provide sticks and guidance to individuals and programs that want to have clinics and or establish or expand lacrosse in their geography | Don, Brian, Phil & Ian | Ian | Year round |  |  | 4000 |  | 1169 | Direct costs include storage unit, shipping sticks and new stick purchases. | YTD rental costs
5 | Non traditional area sport development | Establish one new lacrosse program in a non traditional area | Brian Atwell, Phil Bodenhorn & DTA | PB, CR | Ongoing |  |  |  |  | 1211.16 | Continue 2017 diversity and expansion initiatives. Reach out to Lacrosse community to determine which programs could benefit with financial or material support. Assume D&I grant funds received from USL will be granted out to deserving programs. | Purchased 150 soft sticks & balls for Sacramento area public schools
6 | National team clinics | Provide additional training opportunities for boys & girls in the chapter; expand awareness of chapter's role in supporting lacrosse | TBD - Laura may know someone | DTA & CT | TBD | 8/4 & 5 |  |  |  | 200 | If men & women's national team players are available hold session(s) in NorCal. No income or expenses budgeted. DTA to follow up with Onuva Chowdhury. | Supported USL's National team performance event held in Morgan Hill on 8/4&5; DTA dropped off NCCUSL popup, table, chairs, brochures and wrist band. Carlos Trujillo help promote and was on site.
7 | Constituent support meeting | Develop understanding of key constiuents' needs as a basis for developing the chaper budget | Don |  | June |  |  | 450 |  | 0 | Meeting room and refreshment costs included in travel and meeting expenses | Town hall discussion held at NCJLA summer workshop
8 | Grant for local NorCal National Women's team | Grant monies to partially cover costs associated with sending 2 teams. | Laura | Juliett Mittlemann | April | 2018-05-21 |  | 1350 |  | 1350 | Specific application of funds TBD. For 2017 it covered half of the entry fee for each team. It could cover uniform expenses. Grant amount will depend on participation level. | On 5/21 NCCUSL granted to Juliet Mittleman $1,350 to cover the registration cost for one women's team for the 2018 women's national tournament.
9 | Support Officials' evaluations and officials trainer development programs | Provide funds to men and women officials' organization so trainer officials can take time to evaluate on field officials with the expectation that the level of officiating overall rises. | Andy Still - NCRLA; Tyronne Koen and/or Laura Jennings for Umpire Committee of NCCUSL |  | Mar/Apr |  |  | 2500 |  | 2500 | Assumes $1,500 for NCRLA and $1,000 for NCCUSL Umpire Committee or successor | On 7/16 granted $1,500 to NCRLA for officials training activities. On same date, granted $1,000 to NCCUSL Umpire Committee for women's game training clinic expense coverage.
10 | Support USL All American process | Support USL All American process so local athletes obtain recognition | Amy Harms/Nick Juri/Jerem Stothers/Bruce Dini - dogged by Phil B; Chapter publicity - Torri H | Jennifer Lee/Nick Juri/Jerem Stothers/Bruce Dini - Chapter publicity - Torri H | May/June | [5 empty] | Receipents announced and published on the NorCal website and newsletter in June. | Men's and Women's game All American and Academic All American receipents for Northern, Central and Sacramento regions posted on USL website. DTA requested but never received press releases as of 8/16/2018
11 | Maintain website & newsletter | Broad communications | Torri Horowitz; Dan Miller; Don Aiello | TH, DTA | Jan-Dec |  |  | 500 |  |  | Website - load material and programs; 8 newsletters | Newsletters sent - 1/31 - Coching clinics; 4/12 - Class of 2017 HOF announced; 6/5 2018 HOF & volunteer candidate focus; 6/21 2018 HOF candidate nominations, Peak Performance camp & volunteer
12 | Participate in key league and local lacrosse events, e.g., Girls Play Day or equivalent (Davis and/or TI); NCJLA end of season events (May); NCJLA Delegates mtg (Sept); | Develop and expand awareness of Chapter and USL programs and services | Chapter board members as available |  | Feb, Mar, May, Sept | Feb, Mar, May, Sept |  | 1000 |  |  | Costs would include travel and meeting expenses. Moving the Chapter booth; Production of flyers and chapter logoed giveaways. Stocked items from 2016 would carryover/be available | No booth at NCJLA end of season events; DTA will be at NCJLA Delegates mtg Sept 22.
13 | HOF 2018 class election and recognition dinner | Recognition of HOF recipients; further opportunity to expand the awareness of Chapter | TBD for process; Jeanette for venue; Don, other details | TH, DTA | Sept/Oct | 2018-11-16 | 6400 | 9000 | 20400 | 21400 | 10 inductees; 80 paid guests @ $80 each | Torri Horovitz oversaw election process for 3 inductees for class of 2018. HOF event will have 7 inductees (includes 4 inductees from 2017 class). Plan for 120 recipients. Venue search started by DTA for event to be held late Oct/early Nov. Date for the event set for Friday, Nov 16th. Venue search initiated. Pricing to be reviewed at 9/17 board meeting. 150 guests
14 | Additional board members and committee volunteers | Add 1-3 more board members and key activity volunteers. POCO rep; HS boys and girls reps; board development chair; Events coordinator; | Don | DTA | Ongoing |  |  | 800 |  |  | Shirts, hats, awards, meals | Brian Atwell resigned 12/18/17; Jeanette Fritzky finished her term 5/31/18; Lou Biaggi resigned 8/4/18. Lauren Davenport elected 6/18 and will lead D&I; Carlos Trujillo elected 7/16 and will lead NorCal Lacrosse Convention, assist with D&I and regional growth in southern part of chapter. Cathy Reed to be elected 8/20 and will with Phil Bodenhorn lead regional growth in Sacramento area.
15 | Oversee NorCal Chapter Umpire Committee | Continue UC operations under the chapter through mid-year and then plan to spin it out to its own organization. | Don, Laura, Tyrone (?) & Stephen |  | Jan-June |  | 204500 | 204800 | 226684 | 218262 | For 2018, continue operations. Assist with spin off of UC to separate organization mid year 2018 | NorCal Umpire Committee in great financial shape with net assets of about $21,000 as of July 30th. NorCal Women's Lacrosse Officials incorporated 7/9/2018. Formal cessation of NCCUSL UC operations will transpire with transfer of UC cash assets to NCWLO at 8/20/18 NCCUSL board meeting.
| USL Train NorCal Chapter trainers | Provide Chapter certified level 1 trainers | [8 empty] | Presuming this will be completed in 2017
Deliever Education Training
Support Local Lacrosse Organizations
Fuel the Growth of the Sport
Drive Chapter Visibility
Other